## Blank
Sprint Backlog for Project: Application Development
Story ID | Resource | Story/Task | Time Required | Time Remaining
1 | Lead: Hiroshi Tanaka | User Story: I need to be able to plan my commute to save time and reduce stress.
|  | Task 1: Design and implement the ability to enter usual departure and return time | 4
|  | Task 2: Design and implement the ability to receive the most optimal travel route within 15 minutes. | 6
|  | Task 3: Design and implement the ability to receive real-time updates when conditions change | 5
|  | Task 4: Design and implement the ability to explore alternative forms of transportation options | 4
|  | Task 5: Design and implement the ability to review the justification for each option. | 4
2 | Lead: Hiroshi Tanaka | User Story: I must use the App long-term to optimize my user experience.
|  | Task 1: Design and implement the ability to download the App | 3
|  | Task 2: Design and implement automated App updates | 2
|  | Task 3: Design and implement the ability to provide feedback | 3
|  | Task 4: Design and implement the capability to store and access prior trip information | 2
Task 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5

## Example
Sprint Backlog for Project: Coffee Shop App
Story ID | Resource | Story/Task | Time Required (Hours) | Time Remaining (Hours)
0001 Customer Needs 1 | Lead: Ram | User Story: Easy Access to Orders | 77
| Marvin | Task 1: Develop visible drop-down menu | 20
| Marvin | Task 2: List easy to view pricing for all menu options | 15
| Don | Task 3: Develop secure payment transaction feature | 30
| Mona | Task 4: Develop order confirmation acknowledgement function | 12
Task 5
0002 Employee Needs 1 | Lead: Sally | User Story: Real-Time Access to Orders | 30
| Kyoko | Task 1: Develop visual order confirmation screen | 10
| Priya | Task 2: Program capability to see customer's name | 5
| Priya | Task 3: Clearly display desired order pick-up time | 5
| Harold | Task 4: List any applicable special instructions | 5
| Harold | Task 5: Automatically generate label when order is complete | 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
User Story
Task 1
Task 2
Task 3
Task 4
Task 5
Total Sprint Hours |  |  | 107 | 0

## Burndown Chart
Sprint Progress
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Finish
Planned Completion | 107 | 96 | 85 | 74 | 64 | 53 | 42 | 31 | 20 | 10 | 0
Actual Completion | 107 | 92 | 82 | 71 | 59 | 62 | 50 | 39 | 27