## Review Checklist
Sprint Execution Checklist
The Sprint is normally a 15 or 30 day iteration where a useable and potentially releasable increment of a product is created
Item | Consideration | Accomplished | Not Accomplished | Comments/Notes
1 | Does the team agree with User Stories selected for the Sprint? |  |  | Team agreement is essential. The team must agree they have the capacity or velocity to accomplish all work
2 | Does the team agree with the definitions of "Done"? |  |  | The definition is "Done" is a description of exactly what needs to be accomplished for the Sprint to be successful
3 | Is the Sprint Backlog created and validated by the team? |  |  | The Sprint Backlog is created by the team and defines tasks required to implement all selected User Stories
4 | Are all tasks assigned and equitably distributed? |  |  | The team self-organizes and assigns tasks. Tasks must be equitable. Everyone on the team must have tasks to perform
5 | Is a Sprint Goal established? |  |  | A Sprint Goal describes the work to be accomplished in a short, concise, and motivating manner
6 | Are information radiators to include a Kanban Board and Burndown Chart created to support the Sprint? |  |  | The Kanban Board is the primary means to identify and assign tasks and generates burndown charts to track Sprint progress.
7 | Is the Kanban Board the focus of the Daily Scrum meeting and updated by the team? |  |  | Each team member has a set of tasks, often color-coded, on the Kanban Board. The team updates the board.
8 | Is the Daily Scrum meeting conducted at the same time each day and completed in 15 minutes or less? |  |  | The Daily Scrum meeting asks three questions: What did you do yesterday, what will you do today, and are there any blockers?
9 | Do all team members participate in all Sprint ceremonies? |  |  | Maximum participation is essential to the success of Sprint planning, Sprint execution, and Sprint Review planning
10 | Is conflict managed in a constructive manner? |  |  | All conflicts must be addressed and managed. This includes both functional and dysfunctional conflict
11 | Are "Swarms" established to collectively address and remedy problems? |  |  | A "Swarm" is a method where multiple team members work together to focus on a problem or issue
12 | Are blockers identified during the Daily Scrum meeting and addressed immediately? |  |  | Blockers are identified, posted on the Kanban Board, and addressed immediately
13 | Does the team take time to prepare for the Sprint Review/Demo? |  |  | Time to prepare for the Sprint Review should be taken in the latter stages of the Sprint to ensure success
14 | Is time taken to refine the Product Backlog during the Sprint? |  |  | The team must take time to help the Product Owner refine the Product Backlog and ready User Stories for the next Sprint