## Review Checklist
Sprint Review/Demo Checklist
The Sprint Review is a critical ceremony in Scrum. This checklist provides an overview of best practices to ensure the Sprint Review/Demo is successful
Item | Consideration | Accomplished | Not Accomplished | Comments/Notes
1 | Are all key stakeholders invited and present? |  |  | Includes users, other teams, managers, investors, and customers
2 | Are all members of the development team present? |  |  | The entire development team should be present to show solidarity and answer questions.
3 | Is the Product Goal reiterated to all stakeholders? |  |  | Ensures all stakeholders are aware of the product goal and value in achieving it.
4 | Is the Sprint Review conducted as a working session? |  |  | This is a working session to determine current product development and next steps. Cookies and snacks can add to the "working level" environment.
5 | Is the Sprint review timeboxed? |  |  | A 15-Day Sprint should be timeboxed to last no more than 2-hours.
6 | Does the Product Owner open the meeting and define what is "Done"? |  |  | Focus on what was "Done." Do not focus on what was not done.
7 | Does the development team "demo" what was "Done"? |  |  | Actually demo the functionality that was completed. Solicit questions, feedback, and discussion. Ensure what you present meets the definition of "Done."
8 | Are stakeholders provided an opportunity to "play" with the new functionality? |  |  | Set up multiple workstations so stakeholders can access and test the new functionality.
9 | Is feedback documented? |  |  | This can be the job of the Scrum master or a designated team member.
10 | Do stakeholders "accept" the new functionality? |  |  | The stakeholders must accept the new product. The Product owner and team can make recommendations.
11 | Does the Product Owner discuss the current state of the product Backlog, marketplace changes, and release forecast dates? |  |  | This is critical. Provide status, future goals, and maintain stakeholder motivation and focus.
12 | Do attendees collaborate and discuss what should be accomplished in the next Sprint? |  |  | Stakeholders are engaged and play a role in determining the future work to be performed.
13 | Are budgets and timeframes reviewed? |  |  | The Product Owner ensures there is available budget to continue and validates launch dates.
14 | Is the Product Backlog refined during or after the Sprint review is completed? |  |  | Any changes, additions, or deletions to User Stories must be documented as soon as possible to ensure the next Sprint can be planned.